## Sprint
BASIC KANBAN BOARD TEMPLATE
START DATE | DAYS | PROGRESS | UPDATED BY
2025-06-30 | 5 | 0% | Ettore Farinelli
TEAM MEMBERS ASSIGNED TO TASKS
Ettore Farinelli - EF
KANBAN BOARD
BACKLOG | TO DO | IN PROGRESS | TESTING | COMPLETE | ASSIGNED TO | KANBAN TASK CARD
EF
Details of task to be completed.
HOURS: 0
Details of task to be completed.
HOURS: 0
Details of task to be completed.
HOURS: 0
Details of task to be completed.
HOURS: 0
Specify interfaces/traits for player actions and game events
HOURS: 1,5
Implement use cases for player actions (move, interact, inventory, etc.).
HOURS: 1,5
Write tests for world generation consistency.
HOURS: 1
Implement player movement and interaction
HOURS: 2
Implement inventory system and item management
HOURS: 3
Implement combat or challenge mechanics
HOURS: 2
Implement scoring, progression, or achievement systems
HOURS: 1
Implement Enemy movement and combact system
HOURS: 3
EF
EF
EF
EF
EF
EF
EF