## ARCHIVE
ARCHIVE
CATEGORY | ASSIGNED TO | ACTION | STATUS | PRIORITY | HOURS
Task | Ettore Farinelli | Initialize project repository | Complete | High | 0.5
Task | Ettore Farinelli | Set up build system | Complete | High | 0.5
Research | Ettore Farinelli | Configure continuous integration (CI) and automated testing | Complete | Low | 0.5
Task | Ettore Farinelli | Set up code formatting, linting, and .gitignore | Complete | Medium | 0.5
Content | Ettore Farinelli | Set up documentation system (Jekyll + Just the Docs) | Complete | Low | 0.5
Research | Ettore Farinelli | Define clean architecture folder structure (domain, application, infrastructure) | Complete | High | 0.5
Task | Ettore Farinelli | Define Backlog for the entire project | Complete | High | 1
Feature | Ettore Farinelli | Create initial project documentation and architecture overview | Complete | High | 1
Feature | Ettore Farinelli | Design and document core game loop | Complete | High | 0.5
Feature | Ettore Farinelli | Define main entry point (e.g., CliApp.scala) | Complete | High | 0.5
Feature | Ettore Farinelli | Implement error handling and logging infrastructure | Complete | Medium | 1
Feature | Ettore Farinelli | Set up configuration management (game settings, environment variables) | Complete | Low | 0.5
Feature | Ettore Farinelli | Define Player model and attributes | Complete | High | 1.5
Feature | Ettore Farinelli | Define World model and structure | Complete | High | 1.5
Feature | Ettore Farinelli | Define GameState management | Complete | High | 1
Feature | Ettore Farinelli | Specify interfaces/traits for world generation | Complete | Medium | 1
Feature | Ettore Farinelli | Specify interfaces/traits for player actions and game events | Ready to Start | Medium
Feature | Ettore Farinelli | Implement core domain logic for turn progression, win/loss conditions | Complete | High | 1.5
Feature | Ettore Farinelli | Implement CLI controller for user input/output | Complete | Medium | 1.5
Feature | Ettore Farinelli | Implement main menu navigation (start, help, quit) | Complete | Low | 1.5
Feature | Ettore Farinelli | Implement command parsing and validation | Complete | Medium | 1
Update | Ettore Farinelli | Connect CLI controller to application layer (use case invocation) | Complete | Medium | 1.5
Research | Ettore Farinelli | Add input/output adapters for future UI expansion (e.g., GUI, web) | Complete | Medium | 1
Feature | Ettore Farinelli | Implement use cases for player actions (move, interact, inventory, etc.) | Complete | Medium | 2
Feature | Ettore Farinelli | Implement use cases for world generation and initialization | Complete | Medium | 2
Feature | Ettore Farinelli | Design procedural world generation algorithms (noise, cellular automata, etc.) | Complete | Medium | 3
Feature | Ettore Farinelli | Implement terrain generation (map, tiles, biomes) | Complete | Medium | 1
Feature | Ettore Farinelli | Implement structure/object placement (buildings, dungeons, items) | Complete | Medium | 3
Feature | Ettore Farinelli | Implement deterministic world generation using seeds | Ready to Start | Medium
Task | Ettore Farinelli | Write tests for world generation consistency | Ready to Start | Medium
Feature | Ettore Farinelli | Implement player movement and interaction | Ready to Start | Medium
Feature | Ettore Farinelli | Implement inventory system and item management | Ready to Start | Medium
Feature | Ettore Farinelli | Implement basic AI or NPC logic (if applicable) | Ready to Start | Low
Feature | Ettore Farinelli | Implement combat or challenge mechanics (if part of the design) | Ready to Start | Medium
Feature | Ettore Farinelli | Implement scoring, progression, or achievement systems | Ready to Start | Low
Research | Ettore Farinelli | Set up and maintain automated unit tests for all major systems | Ready to Start | Medium
Research | Ettore Farinelli | Set up integration tests for game loop and world generation | Ready to Start | Low
Research | Ettore Farinelli | Implement property-based tests for procedural systems | Ready to Start | Medium
Task | Ettore Farinelli | Perform manual playtesting and bug tracking | Ready to Start | Low
Task | Ettore Farinelli | Maintain up-to-date developer documentation (architecture, API, setup) | Ready to Start | Low
Update | Ettore Farinelli | Update user/player documentation (how to play, features) | Ready to Start | Low
Content | Ettore Farinelli | Add diagrams and visual aids to docs (architecture, workflows) | Ready to Start | Low
Content | Ettore Farinelli | Document sprint reviews, retrospectives, and major decisions | Ready to Start | Low
Update | Ettore Farinelli | Refine CLI or UI for usability and clarity | Ready to Start | Low
Update | Ettore Farinelli | Add error messages and help screens | Ready to Start | Low
31.5

## RECORD BOOK
RECORD BOOK
SPRINT START | FINISH | SPRINT DAYS | HOURS | NOTES AND COMMENTS
2025-06-09 | 2025-06-13 | 5 | 15
2025-06-23 | 2025-06-27 | 5 | 15
2025-06-30 | 2025-07-04 | 5 | 15
2025-07-07 | 2025-07-11 | 5 | 15
|  | 20 | 60

## Dropdown Keys - DO NOT DELETE
KEY DROPDOWNS - DO NOT DELETE
CATEGORY KEY | PRIORITY KEY | STATUS KEY
Research | High | In Progress
Feature | Medium | Ready to Start
Content | Low | Complete
Task |  | On Hold
Update |  | Testing