## Sprint1
BASIC KANBAN BOARD TEMPLATE
START DATE | DAYS | PROGRESS | UPDATED BY
2025-06-09 | 5 | 40% | Ettore Farinelli
TEAM MEMBERS ASSIGNED TO TASKS
Ettore Farinelli - EF
KANBAN BOARD
BACKLOG | TO DO | IN PROGRESS | TESTING | COMPLETE | ASSIGNED TO | KANBAN TASK CARD
EF
Details of task to be completed.
HOURS: 0
Details of task to be completed.
HOURS: 0
Details of task to be completed.
HOURS: 0
Details of task to be completed.
HOURS: 0
Setup GitHub Actions CI/CD.
- Configure Scala test automation
- Setup changelog generation on master branch pushes
HOURS: 0.45
Project Structure Organization.
- Implement clean architecture folders
- Setup proper package hierarchy
- Configure sbt multi-module if needed
HOURS: 0.30
Jekyll Documentation Setup.
- Install Jekyll with Just-the-Docs theme
- Configure local development environment
- Setup docs folder structure and navigation
HOURS: 0.45
Test Infrastructure.
- Setup ScalaTest with property-based testing
- Configure test mirroring of source structure
- Add initial test examples
HOURS: 0.30
Documentation and Planning.
- Update README with setup instructions
- Document architectural decisions
- Plan next sprint objectives
HOURS: 0.30
EF
Create initial project documentation and architecture overview.
.
HOURS: 1
Design and document core game loop.
HOURS: 0.30
Define main entry point (e.g., CliApp.scala).
HOURS: 0.30
Define GameState management
HOURS: 1.5
Implement error handling and logging infrastructure
HOURS: 1.5
Specify interfaces/traits for world generation
HOURS: 1
Define Player model and attributes
HOURS: 1.30
Define World model and structure
HOURS: 1.30
Set up configuration management (game settings, environment variables)
HOURS: 0.30
Specify interfaces/traits for player actions and game events
HOURS: 1.30
Implement core domain logic for turn progression, win/loss conditions
HOURS: 1
Define Backlog for the entire project
HOURS: 1
EF
EF